## Sheet1
Volt-a-mort
DATE | TASK | WHO | TIME | RESULT
2019-08-09 | Protect proposal
| wire diagram | Clint R. | 30 | done and included in dropbox
| ERD | Jamar S. | 60 | done and included in dropbox
| created project on github (general) | Emily S.
2019-08-15 | mock landing page | Clint R. | 30
2019-08-15 | create project plan | Emily S. |  | group discussion (all members)